## Campaign planning template
Campaign planning template
Why is it important to set out a campaign plan?
Campaign plans are valuable for when you need that extra bit of organization. They help to
prioritize your tasks, identify who'll be working on what aspect of the campaign, sense check task progress, and
keep track of deadlines. A strong campaign plan is important in ensuring you develop a clear set of actions and
goals for the project and are a useful way of monitoring everyone else's progress on the team as well.
We at Product Marketing Alliance have put together this simple template to help you with your campaign planning.
Use it as a benchmark for what you should be aiming for within your campaign, but remember that this is totally
customizable to suit your needs- it's merely here to get you started.
What is a RACI chart?
We've incorporated a RACI chart into this template- it is a responsibility assignment matric which describes the participation by variious
roles in completing tasks or deliverables for a project. It's a super handy way of holding everyone within the project accountable
for certain tasks, and makes project management a lot easier. A RACI chart defines whether the people involved will be
"Responsible", "Accountable", "Consulted", or "Informed".
Links | Notes | Ready to start? | Task | What to include | Priority | Start date | Due date | Responsible | Accountable | Consulted | Informed | Status
Stage one: Planning & research
|  | FALSE | Create campaign brief | -Campaign type/product you’re launching -Key objectives/goals -Campaign/product overview and features -Identify and define target audience -Anticipated challenges and solutions -Identify and outline competitors -Useful resources | High | [6 empty] | Complete
|  | FALSE | Kickoff meeting | Things to discuss in meeting: -Team members’ roles and responsibilities -Developing creative concept -Marketing channels -Budget and finances -Important dates, deadlines, and targets | Medium | [6 empty] | In progress
|  | FALSE | Set up campaign calendar |  | Low | [6 empty] | Overdue
|  | FALSE | Develop/outline how you’ll carry out pre and post launch testing | [8 empty] | Not started
|  | FALSE | Identify/secure stakeholders and vendors | [8 empty] | On hold
Stage two: Campaign prep
|  | FALSE | Plan your messaging/content | [8 empty] | Needs approval
|  | FALSE | Marketing assets
|  | FALSE | Gather customer testimonials
|  | FALSE | Design plan/briefing
Stage three: Marketing launch prep
|  | FALSE | Sales/sponsor outreach
|  | FALSE | Social media campaign
|  | FALSE | Email campaign
|  | FALSE | Public relations | Press releases
Stage four: Pre-launch testing
|  | FALSE | Gather feedback - Stakeholders - Sponsors - Company teams
|  | FALSE | Internal campaign health check | Is the campaign meeting original goals/objectives and everything included within brief? How’s the budget looking? Is everything else going well? What needs improving?
|  | FALSE | A/B testing
|  | FALSE | Results analysis
|  | FALSE | Plan to refine campaign
Stage five: Actual launch
|  | FALSE | Launch campaign
|  | FALSE | Continued advertising/marketing
|  | FALSE | Customer/target market engagement
Stage six: Post launch testing
|  | FALSE | Gather key metrics
|  | FALSE | Evaluation of performance
|  | FALSE | Refine and improve campaign/product for future
P.s. We've got a whole course on Go-to-Market, too. Don't forget to use your members’ exclusive discount code for 10% off.